Habitat House Build #99

641 W. Miller

Angleton, TX

This is the tentative schedule of the work planned for each day of build #99.  Note, the most work for volunteers is during the first 5-6 days of the build, especially on week days.  Towards the end of the build, much of the work is done by contractors and is subject to change.  Please contact James Erskine at jerskine1@att.net for more details.

PREBUILD SCHEDULE

Monday 2/8 (Day –3) - No Meal

Fabricate pre-framing materials (door & window frames, corners & tees) porch & carport beams and porch gable truss

Tuesday 2/9 (Day -2) - No Meal

Set hospitality tent

# Start layout, plates, beams, and precuts

Wednesday 2/10 (Day -1) - No Meal

# Finish layout, plates, beams, and precuts

Cut & build joists & sheath porch gable

Mark wall plates

Take delivery of studs, lumber, tub and shower

BUILD SCHEDULE

Thursday 2/11 (Day 1) – Meal

Build and erect walls

Erect porch & carport beams and posts

Friday 2/12 (Day 2) - Meal

Finish building walls

Square walls

Set roof joists, hip rafters, rafters and jack rafters

Install outside wall sheathing

Saturday 1/13 (Day 3) - Meal

Take delivery of windows and ext. doors

Install ext. doors

Continue setting rafters & jack rafters

Install roof bracing

Set front porch gable and frame

# Install porch lookouts, fascia, etc

Monday 2/15 (Day 4) - Meal

Install blue board on outside walls

Start vinyl siding

Install inside deadwood for drywall and attic stairs

Install roof decking

Tuesday 2/16 (Day 5) - Meal

Continue roof decking

Rough electrical

Rough AC

Install roof felt and dry-in (donated by Galaxy Roofing)

Vinyl siding

Install ext. trim

Wednesday 2/17 (Day 6) - Meal

Delivery of sheet rock & insulation

Start rough plumbing (by contractor)

Install insulation under attic decking and baffles over soffit

Shingles (donated by Galaxy Roofing)

# Vinyl siding

Thursday 2/18 (Day 7) - Meal

Continue rough plumbing (by contractor)

Vinyl siding

Friday 2/19 (Day 8) - No meal

Install gas line (by contractor)

Shingles (donated by Galaxy Roofing)

Wall insulation by Contractor

Inspection – Electrical, Plumbing and Mechanical (Heating, Ventilation &Air Conditioning-HVAC) Rough-in Inspection by city & Insulation Inspection for Energy Star

Saturday 2/20 (Day 9) - No meal

Hang Sheetrock (by contractor)

# Monday 2/22 (Day 10) - No Meal

Tape and mud Sheetrock (by contractor)

Tuesday 2/23 (Day 11) - No Meal

Tape and mud Sheetrock (by contractor)

Wednesday 2/24 (Day 12) - No meal

Tape and mud Sheetrock (by contractor)

Thursday 2/25 (Day 13) - No meal

Texture Sheetrock (by contractor)

Friday 2/26(Day 14) - No meal

Texture Sheetrock (by contractor)

Saturday 2/27 (Day 15) - No meal

Trim – Includes caulking and covering nail holes by home owner and several volunteers from about 3 PM until 7 PM

Sunday 2/28 (Day 16) – Beginning at 2 PM No meal

House Preparation for Interior Painting – Consists of completion of caulking and covering of nail holes (if not completed on Friday), sweeping floors and covering them with brown paper, covering windows with brown paper & plastic, covering bathtub & shower and taping door hinges.   Four to six people are needed for four to six hours. It also includes delivering the primer, paint, paint sprayer and all other needed tools and supplies to the jobsite (house).

Monday 2/29 (Day 17) - No meal

Interior painting (by contractor)

Wednesday 3/2 (Day 18) - No meal

Flooring (by contractor)

Thursday 3/3 (Day 19) - No meal

Cabinets – Four to six volunteers are needed for four to six hours

Friday 3/4 (Day 20) – No Meal

FORMICA in Kitchen & bathroom lavatories (by contractor)

Final Trim

Saturday 3/5 (Day 21) – No Meal

Final electrical

Monday 3/7 (Day 22)

Final plumbing (by contractor)

Tuesday 3/8 (Day 23)

Utility Service Inspection for electricity & gas connection by city

Wednesday 3/9 (Day 24)

Set Air Conditioner condenser and install trim for central A/C & Heat (by contractor)

Saturday 3/12 (Day 25)-No meal.

Tentative date for landscaping.  This is work youth and family groups can do.

Monday 3/14 (Day 26)

# Commission A/C and Heat (by contractor)

Tuesday 3/15 (Day 27)

Blown insulation in attic (by contractor)

Wednesday 3/16 (Day 28)

Certificate of Occupancy inspection by city

Energy Star Final Inspection including door blower test & duct leakage test (by contractor)