**Habitat for Humanity of Southern Brazoria County**

**Typical Volunteer Build Schedule**

**Thursday (Day 1)** – Meal

Build and erect walls

Build porch beams, porch gable(s), garage door frame (if needed)

Erect porch beams and posts

**Friday (Day 2)** - Meal

Square walls

Install ceiling joists, beams & strongbacks

Set roof ridges & hip rafters, rafters and jack rafters

Insulate T’s & mark plumbing in exterior walls

Install outside wall sheathing

**Saturday (Day 3)**- Meal

Install ext. doors

Continue outside wall sheathing

Continue setting rafters & jack rafters

Install purlins & roof bracing

Set front porch gable and brace

Cut rafter tails for fascia

Build shear-walls as needed

Install porch lookouts, barge rafters, & fascia, etc

Install deadwood as needed

**Monday (Day 4)**- Meal

Install blue board on outside walls

Prepare window openings and install windows and trim boards

Start vinyl siding (J-strips & starters)

Build AC platform & walk

Install attic stairs

Install roof decking

**Tuesday (Day 5)**- Meal

Continue roof decking

Rough-in electrical

Vinyl siding

Install ext. trim

**Wednesday (Day 6)**- Meal

Finish roof decking if necessary

Rough-in electrical continued

Install insulation under attic decking and baffles over soffit

Vinyl siding

**Thursday (Day 7)**– Meal

Move sheetrock into house

Install insulation under attic decking and baffles over soffit

Rough-in AC

Vinyl siding

Area cleanup

**Friday (Day 8)**

Complete any remaining tasks due to weather delays, etc.

Rough-in plumbing